## Slide 1
Sprint I |  |  |  |  |  | 
Sprint Duration |  | Start Date: 3rd March 2025 End Date:14th March 2025 |  |  |  | 
Sprint Goal |  | Set up Github repository and project structure; Design database; Design backend framework; Design website UI prototype. |  |  |  | 
 | Mon |  | Tue | Wed | Thu | Fri
Week 3 | Set up Github repository and project structure |  |  | Daily Review | Design backend framework | 
 |  |  |  |  | Design website UI prototype | 
 | Design database |  |  |  |  | 
Week 4 | Design backend framework |  |  |  |  | Daily Review
 | Design website UI prototype |  |  |  |  | 
 | Design database |  |  |  |  | 
Task Distribution |  | Task 1: Daiyan Wu Task 2: Yichuan Zhang, Lekun Liu, Xuning Hu Task 3: Junhao Huang, Ruiyang Task 4: Yiyang Han, Tiantian Ye, Weizhe Sun |  |  |  | 

## Slide 2
Sprint II |  |  |  |  |  | 
Task Distribution |  | Start Date: 17th March 2025 End Date: 28th March 2025 |  |  |  | 
Task Distribution |  | Set up database schema; Implement backend framework and API structure; Develop reusable frontend UI components. |  |  |  | 
 | Mon |  | Tue | Wed | Thu | Fri
Week 5 | Set up database schema |  |  | Daily Review | Set up database schema | 
 | Implement backend framework and APIs |  |  |  | Implement backend framework and APIs | 
 | Develop reusable frontend UI components |  |  |  | Develop reusable frontend UI components | 
Week 6 | Set up database schema |  |  |  | Daily Review | 
 | Implement backend framework and APIs |  |  |  |  | 
 | Develop reusable frontend UI components |  |  |  |  | 
Task Distribution |  | Task 1: Yichuan Zhang, Xuning Hu Task 2: Junhao Huang, Ruiyang Wu, Lekun Liu, Daiyan Wu Task 3: Yiyang Han, Tiantian Ye, Weizhe Sun |  |  |  | 

## Slide 3
Sprint III |  |  |  |  |  | 
Sprint Duration |  | Start Date: 31st March 2025 End Date: 18th April 2025 |  |  |  | 
Sprint Goal |  | Implement core backend logic and connect with database; (Junhao Huang, Ruiyang Wu, Lekun Liu, Daiyan Wu, Yichuan Zhang, Xuning Hu) Develop frontend logic and integrate with backend APIs; (Yiyang Han, Tiantian Ye, Weizhe Sun, Lekun Liu) Set up OSS Object Storage Service. (Yichuan Zhang) |  |  |  | 
 | Mon |  | Tue | Wed | Thu | Fri
Week 7 | Implement core backend logic and connect with database |  |  | Daily Review | Implement core backend logic and connect with database | 
 | Develop frontend logic and integrate with backend APIs |  |  |  | Develop frontend logic and integrate with backend APIs | 
 | Set up OSS Object Storage Service |  |  |  | Set up OSS Object Storage Service | 
Week 8 | Implement core backend logic and connect with database |  |  | Daily Review | Implement core backend logic and connect with database | 
 | Develop frontend logic and integrate with backend APIs |  |  |  | Develop frontend logic and integrate with backend APIs | 
 | Set up OSS Object Storage Service |  |  |  | Set up OSS Object Storage Service | 
Week 9 | Implement core backend logic and connect with database |  |  | Daily Review | Implement core backend logic and connect with database | 
 | Develop frontend logic and integrate with backend APIs |  |  |  | Develop frontend logic and integrate with backend APIs | 
 | Set up OSS Object Storage Service |  |  |  | Set up OSS Object Storage Service | 
Task Distribution |  | Task 1: Junhao Huang, Ruiyang Wu, Lekun Liu, Daiyan Wu, Yichuan Zhang, Xuning Hu Task 2: Yiyang Han, Tiantian Ye, Weizhe Sun, Lekun Liu Task 3: Yichuan Zhang |  |  |  | 

## Slide 4
Sprint IV |  |  |  |  |  | 
Sprint Duration |  | Start Date: 21st April 2025 End Date: 30th April 2025 |  |  |  | 
Sprint Goal |  | Deploy backend & frontend onto the server; Conduct backend functional testing & Fix bugs; Perform UI/UX testing on frontend & Fix display and logic issues; Verify production environment functionality. |  |  |  | 
 | Mon |  | Tue | Wed | Thu | Fri
Week 10 | Daily Review |  | Deploy backend & frontend onto the server | Conduct backend functional testing & Fix bugs |  | 
 |  |  |  | Perform UI/UX testing on frontend & Fix display and logic issues |  | 
Week 11 | Conduct backend functional testing & Fix bugs |  | Verify production environment functionality | Deadline |  | 
 | Perform UI/UX testing on frontend & Fix display and logic issues |  |  |  |  | 
Task Distribution |  | Task 1: Lekun Liu, Daiyan Wu, Yichuan Zhang, Task 2: Junhao Huang, Ruiyang Wu, Lekun Liu, Daiyan Wu, Yichuan Zhang, Xuning Hu Task 3: Yiyang Han, Tiantian Ye, Weizhe Sun Task 4: All team members |  |  |  |